PROGRAM  │  ONE-PAGER 01

Master 90-Day Plan

The gated sequence from studio launch to a defensible go / no-go decision.

PURPOSE

This document is the single source of truth for what happens when during the 90-day Design Studio, what must be true to move from one phase to the next, and what the program will deliberately not attempt. Every other one-pager in this pack plugs into a gate defined here. If a proposed activity does not serve a gate on this page, it is out of scope for the 90 days.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Executive Sponsor |  | A — owns the go / no-go |
| Design Studio Lead |  | R — runs the program day to day |
| JazzX Engagement Lead |  | R — owns vendor-side delivery |
| Head of Underwriting |  | C — owns process and quality truth |
| Model Risk / Compliance |  | C — owns control adequacy |
| Steering Committee |  | I — informed biweekly, decides at gates |

DECISIONS THIS DOCUMENT MAKES

- The studio runs shadow-first: Jazz processes real loans in parallel while humans make every decision, and only graduates to limited live production after Gate 2.

- The program is gated, not calendar-driven. A phase that has not met its gate criteria does not advance because the date arrived; it extends, descopes, or stops.

- The baseline is locked at Gate 1 (Day 30) and is never revised afterward using post-Jazz data. A studio that cannot lock a baseline cannot produce a proof of value.

- The go / no-go decision rule is written and signed before Gate 2 results are visible, to prevent the threshold from moving to fit the outcome.

- Scope is one narrow loan-type slice. Breadth is explicitly deferred to a post-studio scale phase.

THE FRAMEWORK

The gate model

Five gates structure the 90 days. Each gate is a scheduled decision with named attendees, pre-circulated evidence, and only three possible outcomes: Advance, Extend (with a stated number of days and what will be different), or Stop. "Advance with concerns" is not an outcome — a concern either blocks the gate or is logged as a risk and the gate advances cleanly.

| Gate | Day | Question it answers | Evidence required |
| --- | --- | --- | --- |
| G0 | Day 0 | Are we able to start? | Team named and released from BAU Security review signed off Governance body chartered Loan slice selected Baseline instrumentation live |
| G1 | Day 30 | Do we know what "before" looks like? | Locked baseline for labor, quality and cycle-time Minimum 60 observed loans Signed baseline attestation from Underwriting |
| G2 | Day 60 | Is Jazz accurate enough to touch a live loan? | Shadow accuracy vs. thresholds by metric Tuning change log Compliance sign-off for limited live Borrower comms posture agreed |
| G3 | Day 80 | Does it hold up in production? | Live slice quality and cycle-time delta Zero unremediated borrower-impacting defects Ops readiness confirmation |
| G4 | Day 90 | Do we scale, stop, or extend? | Full evidence pack Business case with baseline-to-live comparison Scale plan and its cost Decision against pre-signed criteria |

Phases and the work inside them

| Phase | Days | Core work | Owns |
| --- | --- | --- | --- |
| 0 — Mobilize | −14 to 0 | Charter governance; name and release the team; complete security and third-party risk review; select the loan slice; stand up baseline capture; agree comms posture | Studio Lead |
| 1 — Observe & Baseline | 1–30 | Structured observation of real underwriting and fulfillment; time-and-motion capture; Jazz begins shadow processing ~Day 15; baseline assembled and locked | Studio Lead + UW |
| 2 — Shadow at volume & Tune | 31–60 | Volume shadow processing; weekly tuning of prompts, conditions and document recognition; improvement log maintained; accuracy tracked against thresholds | Studio + JazzX |
| 3 — Limited Live | 61–80 | Narrow slice runs live with 100% human review; borrower and internal comms activated; defect triage in-cycle; ops absorbs the new workflow | Ops + Studio |
| 4 — Evidence & Decision | 81–90 | Evidence pack assembled; business case built; scale plan costed; G4 decision run against pre-signed criteria | Sponsor |

Critical path

Four items carry the whole program. Slippage anywhere else is absorbable; slippage here moves Day 90.

- Security and third-party risk review (Phase 0). The longest-lead dependency in most lenders and the one least under the studio's control. Start it before the SOW is countersigned if procurement allows.

- Data extraction from the LOS into Jazz (Phase 0–1). Shadow processing cannot begin without it, and every downstream day of evidence is lost one-for-one.

- Baseline lock (Gate 1). Cannot be recovered retrospectively once Jazz is influencing the workflow. If Phase 1 slips, extend Phase 1 rather than compressing it.

- Compliance sign-off for limited live (Gate 2). Needs to be socialised from Day 30, not requested at Day 58.

Explicitly out of scope for 90 days

Naming these up front is what protects the timeline. Each is a legitimate ambition deferred to the scale phase, not a rejection.

- Broad loan-type coverage beyond the selected slice

- Full LOS write-back and system-of-record automation

- Removing the human reviewer from any live decision

- Integration with marketing, pricing, or servicing systems

- Headcount reduction — the studio measures labor, it does not act on it

- Custom model development beyond configuration and tuning within Jazz

ARTIFACTS & TEMPLATES

Week-by-week plan

| Week | Milestone | Gate |
| --- | --- | --- |
| Pre −2/−1 | Governance chartered, team named, security review submitted, loan slice selected | → G0 |
| W1 | Kickoff; observation begins; baseline capture instrumented |  |
| W2 | Observation continues; LOS extraction validated; first Jazz test loans |  |
| W3 | Shadow processing begins at low volume; weekly feedback loop starts |  |
| W4 | Baseline assembled, reviewed, attested and locked | → G1 |
| W5–W6 | Shadow volume ramps; first full tuning cycles; improvement log live |  |
| W7 | Mid-phase accuracy read; compliance engagement for live authorisation |  |
| W8 | Accuracy vs. thresholds assessed; live-readiness pack assembled | → G2 |
| W9 | Limited live begins on narrow slice; borrower and internal comms activated |  |
| W10–W11 | Live operation; defect triage; ops absorption; cycle-time measured |  |
| W12 | Live slice performance reviewed | → G3 |
| W13 | Evidence pack, business case and scale plan; decision | → G4 |

Days are relative to kickoff (Day 1), so the calendar can shift without re-cutting the plan.

Dependencies on JazzX

| Dependency | Needed by | Consequence if late |
| --- | --- | --- |
| Environment provisioned and accessible | Day −7 | Kickoff slips one-for-one |
| LOS data extraction working end to end | Day 10 | Shadow start slips; evidence days lost |
| Named tuning engineer available weekly | Day 15 | Tuning cycle stretches; G2 at risk |
| Builder Studio access for our team | Day 30 | Capability transfer fails; vendor dependence at Day 91 |
| Audit-grade output logging | Day 45 | Cannot evidence quality at G2 or satisfy compliance |

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Daily (W1–4) | Observation debrief — 15 minutes, studio team only | Observation log entries |
| Weekly, Thu | Feedback loop — findings, tuning decisions, blockers | Tuning backlog, improvement log |
| Biweekly | Steering committee — progress against gates, risks, decisions needed | Decision record |
| At each gate | Gate review — evidence pre-circulated 48 hours ahead | Advance / Extend / Stop |
| Monthly | Executive readout — one page, no deck | Sponsor briefing |

DEFINITION OF DONE

- All five gates held on the record with a documented Advance / Extend / Stop outcome

- Baseline locked and attested before any Jazz output influenced a live decision

- Go / no-go criteria signed before Gate 2 evidence was visible

- Evidence pack complete enough that someone outside the studio can audit the conclusion

- A costed scale plan exists whether the answer is go or no-go

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Gates become rubber stamps under delivery pressure | Written outcomes with named dissent; Compliance attends every gate and can block | Executive Sponsor |
| Scope creep from adjacent teams who want their loan type included | Out-of-scope list is published and enforced; additions require a steering decision that moves Day 90 | Steering Committee |
| Baseline never locks because "the data is not clean yet" | Baseline is time-boxed to Phase 1 with a documented-limitations clause rather than perfection | Executive Sponsor |
| Vendor dependency at Day 91 — we can operate Jazz but not change it | Builder Studio enablement is a tracked deliverable, not an optional extra | Studio Lead |
| Team pulled back into BAU during peak volume | Named seats with backfill agreed at G0; sponsor re-confirms release at each gate | Executive Sponsor |