LOGISTICS — PRODUCTION READINESS  │  ONE-PAGER 04

Change Management

Getting underwriters and processors to use it, tell the truth about it, and keep doing so.

PURPOSE

To manage the human side of the studio, where most AI pilots actually fail. The technology risk in a 90-day studio is modest and well understood; the adoption risk is not. This document addresses the parallel-run tax, the accountability question, and the specific resistance patterns that appear when experienced credit professionals are asked to work alongside a system that appears to second-guess them.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Head of Underwriting |  | A — owns adoption in the front line |
| Studio Lead |  | R — runs the change plan |
| HR / People |  | C — employment narrative, capacity relief |
| Team leads / supervisors |  | R — daily reinforcement |
| Studio participants |  | R — the change happens through them |

DECISIONS THIS DOCUMENT MAKES

- The parallel-run tax is real and is funded. Shadow mode means doing parts of the work twice. Studio participants receive documented capacity relief; we do not ask for the studio on top of a full pipeline.

- Studio participants are not measured on agreement with Jazz. Their production metrics are held harmless for the studio period, and disagreement is treated as the primary deliverable.

- The accountability question is answered before Day 61: when Jazz is wrong and a human approved it, the human is not penalised provided they followed the documented review process.

- Adoption is measured, not assumed. Usage, feedback volume, and sentiment are tracked weekly as leading indicators of studio validity.

- Participation in the studio is a development opportunity with a named benefit to the participant, stated at selection.

THE FRAMEWORK

The four resistance patterns and what actually works

| Pattern | Sounds like | Root cause | Counter-move |
| --- | --- | --- | --- |
| Expertise threat | "It does not understand a self-employed borrower." | Identity is bound to hard-won judgement | Put them in the tuning seat. An underwriter who has corrected the system owns the result rather than resisting it. |
| Trust deficit | "It was wrong on that file last week." | One salient error outweighs fifty silent successes | Publish accuracy openly, including failures. Log every reported error visibly and show the fix. |
| Workload resentment | "I do not have time for this on top of my pipeline." | Entirely legitimate — shadow adds work | Fund the capacity relief. This is the single highest-leverage intervention available. |
| Blame anxiety | "If I approve what it flagged and it is wrong, whose fault is it?" | Unanswered accountability | Answer it in writing before Day 61 and have the Head of UW say it out loud. |

The parallel-run tax

This deserves its own treatment because underestimating it corrupts the evidence. In shadow mode the underwriter does their normal work and reviews what Jazz produced and records where it differed. Realistically that is an added 15–25% of touch time per studio loan in the early weeks, falling as familiarity grows.

If that time is not funded, participants will rush the comparison step. The studio will then produce quality data that reflects rushed humans rather than the system — and the G2 accuracy read will be wrong in a direction nobody can detect. Fund the relief, and record the actual added time as a studio metric in its own right, because it is a real cost that belongs in the business case.

Adoption plan by phase

| Phase | Change objective | Intervention |
| --- | --- | --- |
| Pre-Day 1 | Awareness and safety | Selection conversation with each participant Written headcount commitment Metrics held harmless confirmed in writing |
| Days 1–30 | Familiarity, not yet performance | Hands-on training with real files Daily 15-minute debrief Explicit permission to be slow while learning |
| Days 31–60 | Ownership through tuning | Participants drive the tuning backlog Visible fixes from their feedback Peer demonstration between participants |
| Days 61–80 | Operating under live conditions | Accountability statement issued Supervisor reinforcement Rapid defect triage so trust is not lost to a slow fix |
| Days 81–90 | Capture and transition | Structured exit interviews with every participant Participants co-present findings at G4 Named next step for each participant |

ARTIFACTS & TEMPLATES

Adoption metrics — leading indicators of studio validity

| Metric | How measured | Healthy signal | Warning |
| --- | --- | --- | --- |
| Comparison completion rate | Studio loans with a recorded human-vs-Jazz comparison | > 95% | Falling — capacity problem |
| Feedback volume | Items raised per participant per week | Steady or rising | Drops to zero — disengagement, not perfection |
| Error reports | Jazz errors flagged by participants | Consistent flow | Zero for a week — nobody is looking |
| Time-to-fix | Days from participant report to resolved or explained | < 7 days | > 14 days kills reporting |
| Participant sentiment | One-question weekly pulse | Stable or improving | Sharp drop after any process change |
| Voluntary use | Once optional, do they still use it? | Rising in Phase 3 | The most honest metric available |

Accountability statement — to be signed by the Head of Underwriting before Day 61

| Question | Answer to be confirmed |
| --- | --- |
| If Jazz is wrong and I followed the review process, am I at fault? | No — documented process followed means no individual fault |
| If I override Jazz and I am right, does that count against me? | No — overrides are expected and are studio data |
| If I override Jazz and I am wrong, what happens? | Normal QC process, unchanged from today |
| Does my studio work affect my production metrics? | No — held harmless for the studio period |
| Who do I tell when something looks wrong? |  |
| What happens to my role after Day 90? |  |

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Daily (Phase 1) | 15-minute debrief — friction, surprises, errors | Observation log |
| Weekly | Participant pulse plus feedback review in the weekly loop | Sentiment trend, tuning backlog |
| Biweekly | Supervisor check-in with each participant, one to one | Individual concerns surfaced early |
| At G2 | Readiness conversation — does the team feel safe going live? | Go / no-go input from the front line |
| At G4 | Exit interviews with every participant | Qualitative findings for the evidence pack |

DEFINITION OF DONE

- Capacity relief documented and actually delivered, not merely promised

- Metrics-held-harmless commitment issued in writing before Day 1

- Accountability statement signed and communicated before Day 61

- Adoption metrics tracked weekly with at least one intervention triggered by them

- Every participant interviewed at exit and their input represented at G4

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Capacity relief promised but not delivered under volume pressure | Sponsor re-confirms release at every gate; comparison completion rate is the early warning | Executive Sponsor |
| Participants tell the studio what it wants to hear | Dissent explicitly framed as the deliverable; anonymous channel available; watch for feedback volume falling | Studio Lead |
| Best performers selected, so results do not generalise | Deliberate mix of experience levels; documented in the evidence pack as a limitation | Head of Underwriting |
| Adoption collapses after one visible Jazz failure | Fast, visible triage; publish accuracy including failures from week one so no single error is a surprise | Studio Lead |
| Studio participants return to BAU at Day 91 with no recognition | Named next step and recognition agreed at selection, delivered at close | HR |