LOGISTICS — DEFINE PROOF OF VALUE  │  ONE-PAGER 06

Baseline, Targets & Success Thresholds

Capturing "before" defensibly, and setting the bar before you can see where the ball landed.

PURPOSE

To produce a baseline that will survive scrutiny from Finance, Risk, and an auditor, and to set the thresholds that define success before results are visible. This is the highest-risk document in the pack: a baseline cannot be reconstructed after Jazz has begun influencing the workflow, and a threshold set after seeing the data is not a threshold.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Finance / FP&A |  | A — attests the baseline |
| Data / BI analyst |  | R — builds and validates the capture |
| Head of Underwriting |  | A — attests operational representativeness |
| Studio Lead |  | R — runs the observation and assembly |
| QC |  | C — quality baseline |
| Executive Sponsor |  | A — signs the thresholds before G2 |

DECISIONS THIS DOCUMENT MAKES

- The baseline is locked at Gate 1 (Day 30) and is never revised afterward using post-Jazz data. Errors found later are documented as limitations, not corrected retroactively.

- The baseline is drawn from the same loan slice, same team, and same season as the comparison period, or the mix difference is explicitly adjusted for and disclosed.

- Thresholds are set at three levels — Minimum, Target, Stretch — and are signed by the Sponsor before Gate 2 evidence exists.

- Where the sample cannot support a statistical claim, the result is reported as directional and labelled as such. The studio does not present underpowered findings as proof.

- Paired comparison is used wherever shadow mode allows it, because it is dramatically more efficient than comparing separate groups.

THE FRAMEWORK

Four sources, triangulated

No single source is sufficient. LOS timestamps are complete but measure elapsed time rather than effort; observation measures effort accurately but covers few loans. Use them together and reconcile the difference explicitly.

| Source | Gives you | Sample | Weakness |
| --- | --- | --- | --- |
| LOS event log | Cycle time, touches, queue time, volumes | All loans, 12 months | Elapsed only; event definitions may have changed historically |
| Structured observation | True touch time by task | 20–30 loans | Small sample; observer effect inflates care |
| QC file review | Defect and quality baseline | Standard QC sample | Lags; sampling may not match the studio slice |
| Participant time diary | Task mix and interruption load | 2 weeks, all participants | Self-reported; use for structure, not for headline numbers |

Sample size — what 90 days can and cannot prove

Be honest about this at G0 rather than discovering it at G4. For rate-type metrics compared across separate groups, the sample sizes required to detect small differences are far larger than a 90-day studio produces. The table below assumes a 20% baseline rate, 5% significance, 80% power.

- Use paired comparison wherever possible. Because shadow runs Jazz on the same loans the humans work, most quality metrics are paired rather than independent — the same file has both a human and a Jazz result. Paired designs typically need a fraction of the sample, and this single design choice does more for the studio's statistical power than any increase in volume.

- Target 150–200 shadow loans as the working plan for the slice, and confirm against the analyst's recomputed numbers at G0.

- Cycle-time cannot be paired — it is measured only in the Phase 3 live period, on a smaller sample, and will almost always be directional rather than conclusive. Plan the narrative for that now.

| Difference to detect | Loans needed per arm | Feasible in 90 days? |
| --- | --- | --- |
| 20% → 5% (large) | ≈ 75 | Yes |
| 20% → 10% (moderate) | ≈ 200 | Only at reasonable volume |
| 20% → 15% (small) | ≈ 900 | No — report as directional |

Indicative two-proportion sizing. Have the analyst recompute using your actual baseline rates at G0.

Mix and seasonality — the silent baseline killer

A baseline taken in one month and a comparison taken two months later differ in more than Jazz. Purchase-refi mix, investor guidelines, staffing levels, volume pressure, and month-end effects all move the metrics. Before locking, the analyst produces a mix comparison and either shows the periods are comparable or states the adjustment applied.

- Compare loan purpose, occupancy, channel, borrower income type and document complexity across periods

- Prefer a 12-month baseline window over a 1-month window where data allows, to average out seasonality

- Flag any guideline, staffing or system change inside the window as a documented limitation

- Where mix differs materially, report the metric both raw and mix-adjusted

ARTIFACTS & TEMPLATES

Baseline record — populate and lock at G1

| Metric | Baseline value | n | Source | Window |
| --- | --- | --- | --- | --- |
| Underwriter touch time / loan |  |  |  |  |
| Processor touch time / loan |  |  |  |  |
| Touches per loan |  |  |  |  |
| Decision turn time |  |  |  |  |
| Condition turn time |  |  |  |  |
| Application to CTC |  |  |  |  |
| Document recognition accuracy |  |  |  |  |
| Condition precision / recall |  |  |  |  |
| False clear rate |  |  |  |  |
| Rework rate |  |  |  |  |
| Post-close defect rate |  |  |  |  |
| Complaints per 100 loans |  |  |  |  |

Threshold structure — signed before G2 evidence exists

| Level | Meaning | Consequence if not met |
| --- | --- | --- |
| Minimum | Below this the studio has failed on that metric | Blocks the gate; triggers Extend or Stop |
| Target | The level the business case assumes | Go remains possible but the business case is re-run at the actual number |
| Stretch | Materially better than the business case | Accelerates scale scope and funding |

Set Minimum for every metric. Target and Stretch are only required for the metrics carrying the business case.

Threshold register — fill in at G0, sign before G2

| Metric | Baseline | Minimum | Target | Stretch |
| --- | --- | --- | --- | --- |
| Underwriter touch time / loan |  |  |  |  |
| Decision turn time |  |  |  |  |
| Document recognition accuracy |  |  |  |  |
| Condition recall |  |  |  |  |
| False clear rate |  | No worse than baseline |  |  |
| Net cost per loan |  |  |  |  |

False clear rate is a guardrail: its Minimum is "no worse than baseline", never an improvement target traded against speed.

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Days 1–10 | Instrumentation built; historical extract validated | Data quality report |
| Days 5–25 | Structured observation across participants and loan types | Observation dataset |
| Day 25 | Baseline assembled; mix comparison produced | Draft baseline |
| Day 28 | Review with Finance, UW and QC; challenge session | Issues resolved or documented |
| Day 30 | Baseline attested and locked at G1 | Signed baseline record |
| Before G2 | Thresholds signed by the Sponsor | Signed threshold register |

DEFINITION OF DONE

- Baseline locked, dated, and attested by Finance and Head of Underwriting

- Sample size and detectable difference stated per metric, not assumed

- Mix comparison produced and any adjustment disclosed

- Known limitations written down at lock time rather than discovered at G4

- Thresholds signed before Gate 2 evidence is visible, with the signature dated

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Baseline never locks because the data is imperfect | Time-boxed to Phase 1; lock with a documented-limitations clause rather than pursuing perfection | Executive Sponsor |
| Thresholds set after seeing results | Signature is dated and held by Finance; unsigned thresholds block G2 | Finance |
| Historical LOS events defined differently than today | Analyst validates event definitions across the window before use | Data analyst |
| Observer effect inflates baseline care and therefore baseline quality | Observe across several days; triangulate against LOS and QC rather than relying on observation alone | Studio Lead |
| Underpowered result presented as proof at G4 | Every metric reported with n and a conclusive/directional label | Finance |
| Sample too small because studio volume was optimistic | Volume tracked weekly from Day 15; shortfall triggers a scope conversation at Day 45, not Day 85 | Studio Lead |