LOGISTICS — COMMERCIAL ALIGNMENT  │  ONE-PAGER 24

Commercial Scope Definition

Named deliverables with quantities and acceptance — because "support as required" is not a scope.

PURPOSE

To define what JazzX is contractually obliged to deliver, what we are obliged to provide, and how either party knows a deliverable is complete. This is distinct from the studio's operational scope: one-pager 10 defines which loans the studio runs, while this document defines what the vendor owes us. Vague scope is the single most common source of mid-studio friction, and it is entirely preventable at contract stage.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Procurement / Vendor Management |  | A — owns the scope schedule |
| Studio Lead |  | R — specifies what is actually needed |
| IT lead |  | C — technical deliverables and dependencies |
| Finance |  | C — links scope to price |
| Legal |  | C — acceptance and remedy language |
| JazzX Engagement Lead |  | C — commits on the vendor side |

DECISIONS THIS DOCUMENT MAKES

- Every deliverable has a named quantity and an acceptance criterion. "Reasonable support", "best efforts" and "as required" are removed from the document.

- People are named, not roled. A commitment to "a solutions engineer" is a commitment to nobody; the studio depends on continuity of the individual who learns our guidelines.

- Enablement is a contracted deliverable with acceptance, not a courtesy. If it is not in scope with a test, it will be the first thing to slip (see one-pager 18).

- Our obligations are in scope too. A one-sided scope lets delivery failures be attributed to us without evidence, and lets our own slippage go unmanaged.

- Anything not listed is out of scope and priced separately — stated explicitly rather than left to inference.

THE FRAMEWORK

JazzX deliverables — the minimum specification

| Deliverable | Quantity / specification | Accepted when |
| --- | --- | --- |
| Environment | Dedicated studio environment, provisioned by Day −7 | Our team can log in and process a test loan end to end |
| Integration support | Named engineer, ___ hours/week through Day 30 | Extraction working and reconciled on real files |
| Tuning engineer | Named individual, ___ hours/week, Days 15–90 | Weekly cycle delivered without slippage |
| Builder Studio access | ___ named users, live by Day 30, including one underwriter | Our users can make and ship a change |
| Structured enablement | ___ sessions, defined syllabus, by Day 30 | Independence assessment passed at Day 85 (one-pager 18) |
| Audit-grade output logging | Live by Day 45 | Any output reconstructible for any studio loan |
| Model change notification | Written notice ___ days before any model change | Notice actually received before a change lands |
| Documentation | Configuration, prompts, mappings — retainable by us | Held in our systems, readable without vendor tooling |
| Escalation | Named contacts, defined response times | Two escalations handled within the stated times |
| Exit support | Data return and deletion within ___ days of notice | Certificate of deletion received |

Our obligations — equally binding

- Named studio team released and available from Day 1 (one-pager 09)

- Environment and network access for the vendor within the agreed security envelope

- Data extraction from our side working to the agreed specification by Day 10

- Named decision-makers available for gate reviews within the scheduled window

- Test data and a defined set of representative loan files for initial configuration

- Timely security review completion — with the caveat that our review cannot be delayed by their late documentation

Explicitly out of scope

Naming these prevents the most common mid-studio dispute, which is not about what was promised but about what was assumed.

- Production-grade hosting, availability guarantees, or SLAs beyond the studio support model (one-pager 22)

- Custom development beyond configuration and tuning within the product

- Integration with any system other than those named in the scope schedule

- Write-back to our system of record unless separately approved at G2 (one-pager 20)

- Training for users outside the named studio team

- Historical reprocessing beyond the agreed holdout and regression sets

- Any commitment on model performance — the studio exists to measure it, not to have it warranted

Change control

- A change request is raised in writing by either party, with the reason and the deliverable affected.

- The Studio Lead assesses whether it is genuinely new scope or a clarification of existing scope — most requests are the latter, and clarifications are not chargeable.

- Genuine scope changes are priced against the agreed rate card before any work begins.

- Anything that moves a gate date requires a Steering decision (one-pager 02), not just a commercial agreement.

- The change register is reviewed at every gate so cumulative drift is visible rather than discovered at the end.

ARTIFACTS & TEMPLATES

Named individuals — the continuity that actually matters

| Role | Named individual | Commitment | Replacement terms |
| --- | --- | --- | --- |
| Engagement lead |  |  | Notice + handover overlap |
| Integration engineer |  |  |  |
| Tuning engineer |  |  |  |
| Enablement lead |  |  |  |

Require a handover overlap for any replacement. A new engineer who has not learned our condition taxonomy costs weeks that the 90 days do not have.

Scope change register

| Change | Raised by | New scope or clarification? | Price | Gate impact |
| --- | --- | --- | --- | --- |

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Pre-G0 | Scope schedule agreed with quantities and acceptance criteria | Signed scope |
| Weekly | Deliverable status reviewed in the working group | Delivery tracking |
| Biweekly | Change register reviewed | Drift visibility |
| At each gate | Deliverables accepted or formally not accepted | Acceptance record |
| At G4 | Final acceptance and any outstanding obligations recorded | Closeout |

DEFINITION OF DONE

- Every deliverable carrying a quantity and an acceptance criterion

- Named individuals with replacement and handover terms

- Our obligations documented alongside theirs

- Out-of-scope list explicit rather than implied

- Change register reviewed at every gate with no undisclosed cumulative drift

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| "Support as required" language leaves the vendor commitment unenforceable | Quantities and acceptance criteria on every line; Legal reviews for vague terms before signature | Procurement |
| Key vendor individual replaced mid-studio | Named individuals with notice and handover overlap terms | Procurement |
| Enablement slips because it is not a contracted deliverable | In scope with acceptance tied to the Day 85 independence assessment | Studio Lead |
| Clarifications repriced as change orders | Studio Lead assesses new-scope vs. clarification before any pricing conversation | Studio Lead |
| Our own late delivery becomes the vendor's defence for missing theirs | Our obligations documented and tracked with the same discipline | Studio Lead |
| Vendor asked to warrant model performance, which they cannot and should not | Performance is measured by the studio, not warranted; stated as out of scope | Legal |