EXECUTION — LAUNCH DESIGN STUDIO  │  ONE-PAGER 08

Launch Design Studio

Standing up a small, protected team that runs real loans through a parallel path.

PURPOSE

To define what the Design Studio actually is as an operating unit: who is in it, what work flows through it, how that work differs from the standard workflow, and how it learns each week. This is the umbrella for one-pagers 09 through 13, each of which details one component. Read this first; the others are the operating detail.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Design Studio Lead |  | A — owns the studio as an operating unit |
| Head of Underwriting |  | A — releases the people, owns process truth |
| Head of Operations |  | C — workflow and capacity impact |
| JazzX Engagement Lead |  | R — vendor-side delivery and enablement |
| Executive Sponsor |  | A — protects the studio from BAU reabsorption |

DECISIONS THIS DOCUMENT MAKES

- The studio is a small, named, protected team — not a committee and not a side-of-desk assignment. Six to eight people with real capacity relief beats twenty with none.

- The studio runs a parallel path: real loans, real files, real conditions, with the standard workflow remaining the system of record throughout the shadow phase.

- The studio is co-located or reliably co-present for at least the first two weeks. Observation and rapid learning do not survive a fully asynchronous start.

- The studio owns its own backlog. Tuning priorities are set inside the weekly loop by the people doing the work, not by a steering committee reading a report.

- The studio is time-boxed to 90 days and either converts to a permanent capability at G4 or dissolves. It does not quietly persist.

THE FRAMEWORK

The five components

| Component | Detail in | The one thing that matters |
| --- | --- | --- |
| Small cross-functional team | One-pager 09 | Named seats with funded capacity relief — not volunteers on top of a full pipeline |
| Loan types and market | One-pager 10 | Narrow enough to reach sample size, representative enough that the result generalises |
| Process design vs. current workflow | One-pager 11 | An unambiguous rule for when a loan leaves the studio and returns to the standard path |
| Weekly feedback loop | One-pager 12 | Every cycle ends with a decision and a visible change, or participants stop contributing |
| Observing real activity | One-pager 13 | Watch what people do, not what the process document says they do |

What a studio loan actually looks like

- A loan matching the slice definition enters the pipeline and is tagged for the studio cohort.

- The file is worked normally by the studio underwriter or processor — the standard workflow is unchanged and remains the system of record.

- In parallel, the file is processed by Jazz: documents recognised, data extracted, conditions proposed.

- The studio participant reviews the Jazz output after forming their own view, so the comparison is not anchored by seeing the answer first.

- Differences are recorded in the comparison log: what Jazz caught that the human did not, what the human caught that Jazz did not, and what Jazz got wrong.

- The human decision stands. Jazz output never reaches the borrower or the file during the shadow phase.

- Differences feed the weekly loop, become tuning items, and are tracked to resolution in the improvement log.

Sequencing that matters

Two ordering decisions do more for evidence quality than anything else in the studio, and both are easy to get wrong under time pressure.

- Human first, then Jazz. If the participant sees the Jazz output before forming a view, anchoring destroys the comparison and the recall measurement becomes meaningless. Enforce it in the workflow, not by asking nicely.

- Observe before you tune. Weeks 1–2 are for watching the current process, not for improving Jazz. Tuning against a misunderstood process bakes in the misunderstanding and is expensive to unwind at Week 8.

ARTIFACTS & TEMPLATES

Studio setup checklist — complete before G0

| Item | Owner | Done |
| --- | --- | --- |
| Team named, released, and capacity relief funded | Head of UW |  |
| Loan slice defined with a written inclusion rule | Studio Lead |  |
| Cohort tagging working in the LOS | IT |  |
| Jazz environment provisioned and accessible | JazzX |  |
| LOS data extraction validated end to end | IT + JazzX |  |
| Comparison log built and tested with a real file | Studio Lead |  |
| Baseline instrumentation live | Data analyst |  |
| Studio space and weekly meeting slot secured | Studio Lead |  |
| Security review signed off | InfoSec |  |
| Kickoff communication delivered | Sponsor |  |

Volume plan — track weekly from Day 15

| Phase | Target studio loans / week | Cumulative | Purpose |
| --- | --- | --- | --- |
| Weeks 3–4 | 5–10 | 10–20 | Prove the mechanics work |
| Weeks 5–8 | 20–30 | 90–140 | Build the quality sample |
| Weeks 9–12 | 15–25 (live slice) | 150–240 | Live evidence and cycle-time |

A shortfall against cumulative target at Day 45 triggers a scope conversation — not a silent hope that volume recovers.

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Daily (Weeks 1–4) | 15-minute standing debrief | Observation log |
| Weekly, Thu | Feedback loop — see one-pager 12 | Tuning backlog, decisions |
| Weekly | Volume and completion-rate check | Trajectory against sample target |
| Biweekly | Steering update | Gate trajectory |
| At gates | Studio evidence contributed to the gate pack | Gate evidence |

DEFINITION OF DONE

- Studio operating with named people and delivered capacity relief

- Comparison log complete for at least 95% of studio loans

- Human-first sequencing enforced in the workflow, not merely requested

- Cumulative loan volume on track to the sample target agreed at G0

- Weekly loop has produced a visible change every week it has run

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Studio reabsorbed into BAU during a volume spike | Sponsor protection; named backfill; release re-confirmed at every gate | Executive Sponsor |
| Participants see Jazz output first and anchor on it | Sequencing enforced in the workflow; spot-checked weekly | Studio Lead |
| Volume too low to reach a usable sample | Weekly tracking from Day 15; scope conversation triggered at Day 45 | Studio Lead |
| Tuning starts before the current process is understood | Weeks 1–2 ring-fenced for observation; no tuning items accepted before Day 15 | Studio Lead |
| Studio persists past Day 90 without a decision | Time-box is in the charter; G4 converts or dissolves it | Steering Committee |