EXECUTION — LAUNCH DESIGN STUDIO  │  ONE-PAGER 12

Weekly Feedback Loop

Ninety minutes a week that converts observation into change.

PURPOSE

To define the operating rhythm that turns what the studio observes into what the studio changes. The weekly loop is the engine of the program: it is where disagreements become tuning items, tuning items become fixes, and fixes become evidence. A loop that produces discussion but no decisions is the most common way a studio quietly stops learning.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Studio Lead |  | A — chairs, owns the backlog |
| Studio participants |  | R — bring the evidence |
| JazzX engagement lead |  | R — owns tuning delivery |
| Compliance liaison |  | C — attends, flags issues early |
| Data analyst |  | R — brings the numbers |

DECISIONS THIS DOCUMENT MAKES

- The loop is 90 minutes, same slot, every week, and it is never cancelled. A cancelled loop is a week of learning lost that cannot be recovered.

- Every session ends with a written decision list with named owners and dates. Discussion without decisions means the session failed.

- The first agenda item is always what changed because of last week's feedback. This is what keeps participants contributing.

- Participants set tuning priority, not the vendor and not the steering committee. The people doing the work know what hurts.

- The loop is a working session, not a status report. Reporting is done in writing beforehand.

THE FRAMEWORK

The 90-minute agenda

| Min | Item | Output |
| --- | --- | --- |
| 0–10 | What changed since last week — every closed item named, with who raised it | Visible responsiveness; the item that sustains participation |
| 10–25 | The numbers — volume, completion rate, accuracy trend, defects | Trajectory against sample and thresholds |
| 25–50 | Case review — two or three specific loans where human and Jazz disagreed | Root cause per case |
| 50–70 | Tuning backlog — prioritise, assign, agree what ships this week | Prioritised backlog with owners |
| 70–80 | Blockers and escalations | Escalation decisions |
| 80–90 | Decisions read back; risks reviewed | Written decision list |

Case review — the highest-value 25 minutes in the program

Pick two or three real files where the human and Jazz disagreed and work them in the room with the file open. Aggregate statistics tell you a metric moved; case review tells you why, and why is what you tune against.

- Rotate case selection between participants so the agenda is not shaped by one person's view

- Deliberately include cases where Jazz was right and the human was wrong — these are the highest-value cases and the least likely to be volunteered

- Drive to a root cause: prompt, source data quality, document quality, guideline interpretation, or genuine model limitation

- Every case ends as a backlog item, a documented "working as intended", or an accepted limitation — never as an unresolved discussion

Backlog discipline

- One backlog, visible to everyone, owned by the Studio Lead

- Every item has a raiser, a category, an owner, and a status

- Items are prioritised on frequency × severity, not on who raised them loudest

- Anything open more than three weeks is either escalated or explicitly closed as "not doing" — silent ageing is what kills reporting

- Closed items are read out by name in the next loop, crediting the person who raised them

ARTIFACTS & TEMPLATES

Tuning backlog fields

| Field | Values |
| --- | --- |
| ID and date raised |  |
| Raised by | Named — credit is the currency of the loop |
| Category | Prompt / condition logic / document recognition / data extraction / integration / process / guideline |
| Frequency | How many loans affected |
| Severity | Sev 1–4 per one-pager 02 |
| Owner | Studio or JazzX |
| Status | Open / in progress / shipped / verified / closed-not-doing |
| Verified by | Who confirmed the fix worked, on which loans |

Weekly one-page report — circulated before the session, not read aloud in it

| Section | Content |
| --- | --- |
| Volume | Studio loans this week and cumulative vs. target |
| Data quality | Comparison completion rate; sequencing spot-check result |
| Accuracy | Trend on the headline quality metrics, with n |
| Backlog | Opened, shipped, verified, ageing |
| Defects | New defects by severity and status |
| Sentiment | Weekly pulse result |
| Risks | Changes to the risk register |

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Daily (Weeks 1–4) | 15-minute standing debrief while observation is fresh | Observation log entries |
| Weekly, Thu 90 min | The feedback loop | Written decision list, prioritised backlog |
| Weekly, Fri | One-page report issued to Steering and participants | Weekly report |
| Biweekly | Backlog health review — ageing items escalated or closed | Cleaned backlog |
| At gates | Loop output rolled into the gate pack | Improvement log, decision history |

DEFINITION OF DONE

- Loop ran every week without cancellation

- Every session produced a written decision list with owners and dates

- Every session opened with what changed from participant feedback

- No backlog item aged past three weeks without escalation or explicit closure

- Case reviews included cases where Jazz outperformed the human

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Loop becomes a status meeting | Written report circulated beforehand; agenda is working items only; decision list mandatory | Studio Lead |
| Cancelled under delivery pressure | Never cancelled — reduced to 30 minutes if genuinely necessary, but held | Studio Lead |
| Participants stop raising items because nothing visibly changes | The first agenda item exists precisely to prevent this; falling feedback volume is the early warning | Studio Lead |
| Vendor drives the agenda toward what is easy to fix | Participants set priority; JazzX delivers against it | Studio Lead |
| Only failure cases reviewed, producing a distorted picture | Deliberate inclusion of cases where Jazz was right and the human was wrong | Senior underwriter |