EXECUTION — TUNE IN JAZZ  │  ONE-PAGER 17

Next Technology Changes & Build Start

Turning studio findings into a costed engineering backlog — and starting the safe parts now.

PURPOSE

To convert what the studio learns into a concrete, costed technology roadmap, and to start building the items that are worth building regardless of the Gate 4 outcome. Without this, the studio ends with a recommendation and no execution path, and the three months of insight decay while a scale plan is written from scratch.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| IT / Engineering lead |  | A — owns the technical roadmap |
| Studio Lead |  | R — supplies the findings and priorities |
| JazzX engagement lead |  | C — vendor-side roadmap dependencies |
| Enterprise architecture |  | C — fit with the target state |
| Finance |  | C — costs the roadmap for the business case |

DECISIONS THIS DOCUMENT MAKES

- Findings are triaged into tune / build / vendor / accept — four fundamentally different responses that are routinely conflated.

- Build work starts during the studio only for items that are no-regret: valuable whether or not Jazz is adopted.

- Anything Jazz-specific waits for Gate 4, so a no-go does not strand sunk engineering cost.

- Every roadmap item is costed and sequenced before Gate 4, so the scale decision is made with a real number rather than an intention.

- Vendor roadmap dependencies are written into the record with dates, and unconfirmed dependencies are treated as risks, not plans.

THE FRAMEWORK

Triage — four responses, not one

| Response | When | Owner | Timing |
| --- | --- | --- | --- |
| Tune | Fixable within Jazz configuration | Studio | This week |
| Build | Needs work in our systems — integration, data quality, workflow | IT | No-regret now; the rest post-G4 |
| Vendor | Needs a JazzX product change | JazzX | Their roadmap, tracked with dates |
| Accept | Not economic to fix; the workflow absorbs it | Studio | Documented as a limitation |

Misfiling a Build item as a Tune item produces weeks of futile prompt engineering. This triage is worth doing carefully.

No-regret build items — safe to start during the studio

These generally pay for themselves through better data and cleaner process regardless of the Gate 4 outcome, and they are the reason a no-go studio still returns value.

- Document capture quality at the source — better scans and better borrower upload guidance improve every downstream process, AI or not

- Data quality remediation in the LOS — the studio will expose field-level inconsistencies that have been quietly costing money for years

- Event instrumentation — the measurement built for the baseline is worth keeping permanently

- Document taxonomy standardisation — a consistent naming and classification scheme benefits every system that touches documents

- Guideline clarification — every ambiguity the studio surfaced in trying to encode a rule is a real ambiguity affecting human underwriters today

Wait-for-Gate-4 items

- LOS write-back and system-of-record automation

- Production-grade integration hardening and scaling

- Any workflow redesign predicated on Jazz being present

- Jazz-specific monitoring, alerting and support tooling

- Expansion of data flows to the vendor

ARTIFACTS & TEMPLATES

Technology roadmap — costed before Gate 4

| Item | Triage | Value | Effort | Depends on | Start |
| --- | --- | --- | --- | --- | --- |
|  | Tune / Build / Vendor / Accept | H / M / L | Days |  | Now / Post-G4 |

Populated continuously from Day 15; costed and sequenced by Day 80 so Gate 4 has a real number.

Vendor roadmap dependencies — track explicitly

| Capability needed | JazzX committed date | Confirmed in writing? | Fallback if late |
| --- | --- | --- | --- |

An uncommitted vendor date is a risk on the register, never a line in the plan.

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Weekly | New findings triaged into the four categories | Updated roadmap |
| Biweekly | Engineering review of build items with IT | Effort estimates |
| Day 45 | No-regret build items started | Work in progress |
| Day 70 | Roadmap costed and sequenced | Draft scale roadmap |
| Day 80 | Roadmap finalised for the Gate 4 pack | Costed roadmap |

DEFINITION OF DONE

- Every studio finding triaged into tune / build / vendor / accept

- No-regret items started and progressing by Day 45

- Full roadmap costed and sequenced before Gate 4

- Vendor dependencies documented with dates and written confirmation status

- No Jazz-specific engineering committed before the Gate 4 decision

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Build work starts on Jazz-specific items and is stranded by a no-go | No-regret test applied before any build starts; Steering approves exceptions | IT lead |
| Roadmap not costed, so Gate 4 decides on an intention | Costing is a Day 80 deliverable and a Gate 4 evidence requirement | Finance |
| Vendor roadmap promises treated as plan | Written confirmation required; unconfirmed items sit on the risk register with fallbacks | Studio Lead |
| Build items misfiled as tuning items | Root-cause discipline in one-pager 15; IT reviews the triage biweekly | IT lead |
| Data quality work deferred and undermines everything downstream | Explicitly listed as no-regret and started at Day 45 | IT lead |