LOGISTICS — PRODUCTION READINESS  │  ONE-PAGER 27

Security Review

The longest-lead dependency in the whole programme. Start it before the contract is signed.

PURPOSE

To get the security review completed in time to start on Day 1, without cutting anything that matters. In most lenders this review is the single longest-lead item in the studio — routinely six to ten weeks — and it is largely outside the studio team's control. Treating it as a Phase 0 formality is the most reliable way to lose a month before the programme has begun.

OWNER & RACI

| Role | Who (fill in at G0) | R / A / C / I |
| --- | --- | --- |
| Information Security |  | A — owns the review and the decision |
| Third-Party Risk |  | R — vendor assessment |
| IT / integration engineer |  | R — our side of the architecture |
| Studio Lead |  | R — drives the schedule and unblocks |
| Privacy / Data Protection |  | C — personal data assessment |
| Procurement |  | C — contractual security obligations |

DECISIONS THIS DOCUMENT MAKES

- The review starts before the SOW is countersigned. Vendor documentation can be requested and assessed under NDA while commercial terms are still being negotiated.

- The review is scoped to what the studio actually does — a narrow, read-only, non-production-writing integration — rather than to a hypothetical full deployment. Reviewing the eventual scale architecture delays the studio by weeks and assesses a design that does not exist yet.

- Workstreams run in parallel, not in sequence. Vendor posture, data flow assessment, and our own integration review have different owners and no dependency on each other.

- Conditional approval with compensating controls is an acceptable outcome and should be actively sought where a finding does not bear on the studio's actual data flows.

- Any change to data scope, or any approval of write-back at G2, triggers a re-review — scoped to the delta, not a restart.

THE FRAMEWORK

Three parallel workstreams

| Workstream | Assesses | Owner | Typical duration |
| --- | --- | --- | --- |
| Vendor security posture | JazzX's own controls: SOC 2 Type II, pen test results, vulnerability management, personnel security, subprocessors | Third-Party Risk | 3–6 weeks, mostly waiting on documents |
| Data flow and privacy | What personal data leaves us, why, where it goes, how long it is held, lawful basis and any privacy assessment required | InfoSec + Privacy | 2–4 weeks |
| Our integration | The trigger, the extraction path, credentials, network exposure, logging, and the read-only property | InfoSec + IT | 2–3 weeks |

Run all three from day one. Sequencing them is what turns a six-week review into a twelve-week one.

Document pack — request on day one

Most of the elapsed time in a vendor security review is waiting for documents. Request everything at once, with a deadline, rather than discovering a gap in week four.

- SOC 2 Type II report (current, with any bridge letter) — or ISO 27001 certificate and statement of applicability

- Most recent penetration test summary and remediation status

- Architecture and data flow diagrams for the services we will use

- Subprocessor list, including any third-party model providers

- Data location, retention and deletion practices

- Encryption in transit and at rest, and key management approach

- Access control model — who at the vendor can access customer data, and how that access is logged

- Incident response process and notification commitments

- Business continuity and disaster recovery plans, with test results

- Personnel security: background checks, training, offboarding

- AI-specific: training data practices, model hosting, whether customer data leaves their environment for inference

Compressing without cutting

- Start under NDA before signature. Nothing about assessing a security posture requires an executed SOW.

- Scope to the studio's real architecture — read-only, no write-back, a named narrow data set, a fixed 90-day period. Say this explicitly in the review request so the reviewer is not assessing an imagined production rollout.

- Pre-brief InfoSec on the gate model so they understand that G2 is a second, narrower decision point and they are not being asked to approve everything now.

- Assign a single named coordinator on our side. Reviews stall in handoffs far more often than in analysis.

- Escalate document delays commercially. A vendor slow to produce a SOC 2 during a sales process will not be faster later; make it a scope obligation (one-pager 24).

- Seek conditional approval where a finding is real but does not touch the studio's data flows, with the condition attached to G2 rather than blocking Day 1.

Common blockers, pre-empted

| Blocker | Pre-empt by |
| --- | --- |
| SOC 2 is out of date or scoped to different services | Ask for scope and period on day one; a bridge letter may suffice |
| Subprocessor list includes an unassessed model provider | Ask specifically about third-party model providers — this is the fourth-party risk regulators focus on |
| Customer data leaves the vendor environment for inference | Ask directly and early; the answer changes the whole assessment |
| No answer on training-data use | Resolve contractually (one-pager 25) as well as technically |
| Our own integration design is not final | Review the design, not the code; design is stable long before build completes |
| Reviewer assumes production scale and full write access | State the studio architecture and its 90-day limit explicitly in the request |

ARTIFACTS & TEMPLATES

Review tracker — status visible weekly from Day −45

| Item | Owner | Requested | Received | Status |
| --- | --- | --- | --- | --- |
| SOC 2 Type II |  |  |  |  |
| Penetration test summary |  |  |  |  |
| Data flow diagram |  |  |  |  |
| Subprocessor list |  |  |  |  |
| Encryption and key management |  |  |  |  |
| Vendor access control model |  |  |  |  |
| Incident response and notification |  |  |  |  |
| BCP / DR with test results |  |  |  |  |
| Training data practices |  |  |  |  |
| Our integration design review |  |  |  |  |
| Privacy assessment |  |  |  |  |

Approval record

| Field | Entry |
| --- | --- |
| Scope approved | Read-only, 90 days, named data classes, no write-back |
| Outcome | Approved / conditionally approved / not approved |
| Conditions and their due dates |  |
| Compensating controls required |  |
| Findings accepted as residual risk |  |
| Risk acceptance signed by |  |
| Re-review triggers | Data scope change; write-back approval at G2; scale decision at G4 |
| Approval date and expiry |  |

CADENCE

| When | What happens | Output |
| --- | --- | --- |
| Day −45 | Review initiated under NDA; full document pack requested | Review open |
| Weekly | Tracker reviewed; delays escalated commercially | Status |
| Day −14 | Findings consolidated; conditions negotiated | Draft outcome |
| Day −7 | Approval or conditional approval issued | Signed approval |
| At G2 | Re-review of the delta if write-back or new data classes are proposed | Delta approval |
| At G4 | Full review refreshed for production scale | Scale approval |

DEFINITION OF DONE

- Review started before SOW countersignature

- All three workstreams run in parallel with a single named coordinator

- Approval scoped explicitly to the studio architecture and its 90-day limit

- Conditions and compensating controls documented with owners and dates

- Re-review triggers agreed in advance so G2 is not a surprise

RISKS & ESCALATION

| Risk | Mitigation | Escalates to |
| --- | --- | --- |
| Review starts after signature and consumes the first month | Initiated under NDA at Day −45; treated as the critical path in one-pager 01 | Studio Lead |
| Reviewer assesses a production-scale architecture that does not exist | Studio architecture and 90-day scope stated explicitly in the review request | InfoSec |
| Vendor slow to produce documents | Full pack requested on day one with a deadline; delivery made a scope obligation | Procurement |
| Third-party model provider discovered late as an unassessed fourth party | Subprocessor and model-provider question asked explicitly in the first request | Third-Party Risk |
| Approval granted for the studio and assumed to cover scale | Approval scoped and dated; re-review triggers named at approval time | InfoSec |
| Write-back approved at G2 without security involvement | Re-review is a stated precondition of any write-back decision (one-pager 20) | InfoSec |