## Slide 1
JazzX Design Studio
A 90-Day Implementation Framework
From studio launch to a defensible go / no-go decision — gated, shadow-first, and measured against a baseline locked before anything changes.
G0
G1
G2
G3
G4
Five gates. Each one a decision, not a checkpoint.
Prepared for the lender programme team · Confidential — no external circulation before G4
Notes: Lender-side framework. Shadow-first: Jazz runs in parallel on real loans while humans decide everything, graduating to a narrow live slice only after Gate 2.

## Slide 2
What this studio has to produce
Three outputs. Everything in the framework serves one of them.
1
A defensible number
What Jazz is worth per loan, net of licence, integration and the review overhead the new workflow adds — computed by Finance, not by the studio.
2
A decision nobody can relitigate
Criteria signed before the evidence exists, must-pass conditions that no score can override, and a pre-costed consequence for every outcome including Stop.
3
A capability we keep
A team that can tune, diagnose and extend Jazz on Day 91 without the vendor in the room — or a priced dependency we entered with our eyes open.
A studio that cannot produce a credible no-go was never producing evidence.
Notes: The third output is the one most pilots skip and most regret at scale.

## Slide 3
The gate model
Each gate is a scheduled decision with three outcomes: Advance, Extend, or Stop.
G0
Day 0
Are we able to start?
Team named and released
Security signed off
Governance chartered
Slice selected
G1
Day 30
Do we know what "before" looks like?
Baseline locked
60+ loans observed
Attested by Underwriting
G2
Day 60
Accurate enough to touch a live loan?
Shadow accuracy vs. thresholds
Tuning change log
Compliance sign-off
G3
Day 80
Does it hold up in production?
Live quality + cycle-time
Zero open borrower defects
Ops readiness
G4
Day 90
Scale, narrow, extend or stop?
Full evidence pack
Business case
Costed scale plan
G1 and G4 are the two that cannot be compressed: a baseline cannot be rebuilt after the fact, and a decision without pre-signed criteria is an argument.

## Slide 4
Ninety days, five phases
Gated, not calendar-driven — a phase that has not met its gate does not advance because the date arrived.
0
Mobilize
−14 to 0
Team, governance, security review, slice selection, baseline instrumentation
1
Observe & Baseline
Days 1–30
Structured observation of real work; shadow starts ~Day 15; baseline locked
2
Shadow & Tune
Days 31–60
Volume shadow processing; weekly tuning cycle; accuracy tracked to threshold
3
Limited Live
Days 61–80
Narrow slice live with 100% human review; comms activated; defect triage
4
Evidence & Decision
Days 81–90
Evidence pack, business case, costed scale plan, G4 decision
Phase 3 is the only place genuine cycle-time evidence exists — which is why it is the phase to protect when the schedule tightens.

## Slide 5
Shadow first, then a narrow live slice
The human decides every loan through Day 80. That is the studio's primary control.
SHADOW
Days 1–60
Jazz processes real loans in parallel; output never reaches the file or the borrower
Human forms a view first, then reviews Jazz — enforced by timestamp, because anchoring destroys the measurement
Differences recorded in the comparison log — the studio's primary data artifact
Borrower experience and SLAs identical to today
LIMITED LIVE
Days 61–80 · authorised at G2
Jazz output enters the file as a clearly labelled proposal
100% human review — no sampling; nothing stands unless affirmatively accepted
Every rejection captured with a reason; adverse-action language stays human-authored
Enhanced QC sampling on the cohort; defects triaged within one business day
A loan leaves the studio immediately if an SLA is at risk, a borrower is affected, or the underwriter simply judges it is not serving the file — no justification required.

## Slide 6
Scope: one narrow slice
Narrow enough to reach a usable sample, standard enough that the result generalises.
150–200
loans through shadow
Below this the statistics do not support a conclusion. Volume is validated against 12 months of actuals before G0 and tracked weekly from Day 15.
Typical first slice
Conventional conforming
W-2 salaried borrowers
Purchase or rate-term refinance
Owner-occupied, single-family
Retail channel
Top three states by volume
Deliberately excluded
Self-employed / complex income
Non-QM, jumbo, portfolio
Government lending (FHA/VA/USDA)
Construction and renovation
States with distinct AI rules
New channels or new teams
The objection that this segment is "already easy" misreads the purpose: the studio establishes whether Jazz works and what it is worth — not how hard a test it can survive.

## Slide 7
A small, protected team
Six to eight named seats with funded capacity relief — not volunteers on top of a full pipeline.
Design Studio Lead
100%
Full time. Not a 20% role.
Senior underwriter
50–75%
A respected sceptic, not an enthusiast
Second underwriter
50%
Different tenure — finds different failures
Senior processor
50%
Owns document and condition reality
Data / BI analyst
50%
Must defend numbers to Finance
IT / integration
25–50%
Named LOS access, not a ticket queue
Compliance liaison
10–20%
Weekly, not just at gates
JazzX engagement lead
Per SOW
Named individual, contracted presence
Capacity relief that exists only on paper is the single most common cause of studio failure — shadow mode adds 15–25% touch time per loan before it removes any.

## Slide 8
What we measure
Three value families, plus a guardrail set that must not degrade.
Labor
Underwriter touch time per loan
Processor touch time
Touches per loan
Condition clearing effort
Review overhead — the new cost
Touch time, never headcount. Elapsed time is not touch time.
Quality
Document recognition accuracy
Data extraction accuracy, weighted
Condition precision and recall
False clear rate
Rework and post-close defects
False clears and false conditions are not symmetric. Separate thresholds.
Cycle-time
Decision turn time
Condition turn time
Application to CTC
Queue / dwell time
Touch vs. waiting ratio
Shadow cannot measure this. Only Phase 3 produces real evidence.
GUARDRAILS — must not degrade
Credit quality · Fair lending · Borrower complaints · Employee sentiment · Investor & agency compliance · Data security
A breach blocks the gate regardless of how strong the headline numbers are.

## Slide 9
The baseline is the critical path
Not the integration. Not the tuning.
A baseline cannot be reconstructed after Jazz begins influencing the workflow.
Locked at G1
Day 30, attested by Finance and Underwriting, never revised afterward using post-Jazz data
Four sources
LOS events, structured observation, QC review, participant time diary — triangulated, never one alone
Paired where possible
Shadow runs Jazz on the same loans humans work, so most quality metrics are paired — far more powerful than comparing separate groups
Honest about power
Detecting a 20%→15% shift needs ~900 loans per arm. Report what the sample supports and label the rest directional
If Phase 1 slips, extend Phase 1 — never compress it.

## Slide 10
The weekly loop
Ninety minutes that convert observation into change. Never cancelled.
0–10
What changed
Every item closed since last week, named with who raised it. This is what keeps people contributing.
10–25
The numbers
Volume, completion rate, accuracy trend, defects — trajectory against sample and thresholds.
25–50
Case review
Two or three real loans where human and Jazz disagreed, worked with the file open. The highest-value 25 minutes in the program.
50–70
Tuning backlog
Prioritise on frequency × severity, assign owners, agree what ships this week.
70–90
Blockers, then decisions read back
A session that produces discussion but no written decision list has failed.
Deliberately include the cases where Jazz was right and the human was wrong — the highest-value cases, and the least likely to be volunteered.

## Slide 11
Tuning — and the capability we keep
If only JazzX can change it at Day 91, we bought a service, not a capability.
Days 1–15
Watch
JazzX makes changes; we observe and ask. No expectation of independence.
Days 16–30
Specify
We write the change specification; JazzX implements. Builds precision before mechanics.
Days 31–45
Pair
We drive with JazzX alongside. Builder Studio access live for 3+ named people.
Days 46–70
Do
We implement; JazzX reviews. Every change is ours.
Days 71–90
Own
JazzX on escalation only. Independence formally assessed at Day 85.
Measurement discipline
One substantive change per surface per cycle — or the effect cannot be attributed
Weekly freeze, version tag on every studio loan, full regression set every cycle
A clean holdout of 30–40 early loans, never tuned against
Re-run at Day 45, 60, 85 — the only way to separate real improvement from us getting used to it

## Slide 12
The Day 90 decision
Four outcomes, not two. Criteria signed before the evidence exists.
Eight must-pass criteria
Absolute. No weighted score, however strong, overrides a failure.
No unremediated borrower-impacting defect
False clear rate no worse than baseline
Compliance sign-off for production use
Model risk validation satisfied to tier
Adverse-action articulability demonstrated
No adverse fair lending pattern
Zero unresolved security incidents
Vendor viability acceptable at scale
Scale
All must-pass clear, weighted ≥ 3.5
Budget released to the pre-agreed figure; team stood up in 30 days
Narrow
Value concentrated in part of the slice
Production use continues only where value was proven; contract right-sized
Extend
Genuinely inconclusive, not disappointing
One use only, 60 days maximum, written statement of what will differ
Stop
Any must-pass fails, or weighted < 2.5
Defined end date, contract exit, findings published, team recognised
If the Stop row cannot be costed at G0, the organisation is not running a studio — it is running a rollout with a pilot label.

## Slide 13
What will actually go wrong
The five failure modes worth designing against now.
1
Capacity relief exists on paper only
Participants rush the comparison step; the quality data reflects hurried humans, and the G2 read is wrong in a direction nobody can detect.
Implemented in assignment rules; comparison completion rate watched weekly
2
The baseline never locks
"The data is not clean yet" becomes permanent, and at Day 90 there is nothing to compare against.
Time-boxed to Phase 1; lock with documented limitations rather than chasing perfection
3
Thresholds move to fit the result
The decision becomes an argument about what counts as success.
Signed and dated before G2 evidence exists; held by Finance
4
Anchoring contaminates the comparison
Participants look at Jazz first when busy; recall measurement becomes meaningless.
Enforced by timestamp, spot-checked weekly, contaminated entries excluded
5
Capability never transfers
At Day 91 only JazzX can change anything, and the scale decision carries an unpriced dependency.
Tracked deliverable with a formal Day 85 independence assessment
Failure mode
Why it matters
Countermeasure

## Slide 14
The framework pack
22 one-pagers, each with purpose, RACI, decisions, framework, templates, cadence, definition of done and risks.
Program
01 Master 90-Day Plan
Logistics — Production Readiness
02 Governance Structure
03 Borrower & Internal Communications
04 Change Management
Logistics — Define Proof of Value
05 Define What Value Looks Like
06 Baseline, Targets & Thresholds
07 Go / No-Go Decision Criteria
Execution — Launch Studio
08 Launch Design Studio
09 Small Cross-Functional Team
10 Loan Types & Market Selection
11 Studio vs. Current Workflow
12 Weekly Feedback Loop
13 Observing Real Underwriting
Execution — Tune in Jazz
14 Tune in Jazz
15 Refining Prompts & Recognition
16 Documenting Improvement
17 Next Technology Changes
18 Builder Studio & Nuggets
Technology — Integrate & Deploy
19 Triggering Loans to Jazz
20 LOS Extraction & Write-Back
21 MU Conditions Integration
22 Minimum-Change Deployment
Every template in the pack has fill-in fields rather than assumed answers — the slice, the roster, the thresholds and the decision rule are yours to set at G0.

## Slide 15
What we need to start
Eight decisions and one signature stand between here and Day 1.
Named sponsor
One executive accountable for the go / no-go
Team released
Six to eight seats with funded capacity relief
Slice selected
Written inclusion rule, volume validated against 12 months
Governance chartered
Steering, Working Group, control functions with block rights
Security review started
The longest-lead dependency — start before the SOW is countersigned
Baseline instrumented
Measurement live before the first shadow loan
Thresholds drafted
Signed before G2 evidence exists
Stop pre-costed
Exit terms and data return agreed while nobody is invested in the answer
G0
G1
G2
G3
G4
Gate 0 is the only one we control entirely. Everything after it is evidence.
Notes: Close on the ask. G0 readiness is entirely within the lender's control; every later gate depends on evidence the studio has to earn.